## 2011
PlayUp Live Marketing Production Plan
PlayUp Offering
PlayUp Story/Theme |  |  |  | July |  |  |  | August |  |  |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December
Dates |  | DEFINITION | 2011-06-27 | 2011-07-04 | 2011-07-11 | 2011-07-18 | 2011-07-25 | 2011-08-01 | 2011-08-08 | 2011-08-15 | 2011-08-22 | 2011-08-29 | 2011-09-05 | 2011-09-12 | 2011-09-19 | 2011-09-26 | 2011-10-03 | 2011-10-10 | 2011-10-17 | 2011-10-24 | 2011-10-31 | 2011-11-07 | 2011-11-14 | 2011-11-21 | 2011-11-28 | 2011-12-05 | 2011-12-12 | 2011-12-19 | 2011-12-26
Events |  |  | 2011-07-11: PlayUp Live Launches on Iphone; 2011-08-15: PlayUp Live Launches on remaining app platforms; 2011-08-29: NCAA Season begins (9/1/11); 2011-09-05: NFL Opening Week ( Sept. 8 - Kickoff Wknd); 2011-09-26: MLB Regular Season Ends (9/28); 2011-10-03: NHL Opening Week; 2011-10-17: MLB World Series; 2011-10-31: NBA Opening Week / Halloween; 2011-11-21: Thanksgiving; 2011-12-19: Christmas
SOCIAL MEDIA
Facebook
| Page | Allows PlayUp to stay connected with people throughout the day by creating experiences, building relationships, and leveraging "word of mouth" marketing
| Content-wall | Post interesting content (messaging, contests, photos, videos, etc.) with clear calls to action that encourage interaction and sharing | Daily - will continue current strategy | Daily | Daily | Daily | Daily | Daily | Daily- begin 'hype up' for the launch of live | Daily- links to download live & hype. Like Athletes PlayUp tweets/posts | Daily- push live as the must have app for NCAA & NFL season | Daily- post on campus events & on Major PR event happening this week | Daily- push Live with NFL opening | Daily | Daily | Daily | Daily | Daily | Daily | Daily | Daily | Daily | Daily | Daily | Daily | Daily | Daily | Daily | Daily
| Branding/Pictures | Bring brand personality to life through an authentic and consistent brand voice. Feature contest winners, new products, new games, events, talent, etc. | Daily - will continue to be "fun+social+sports+unique" within all posts | Daily | Daily | Daily | Daily | Daily | upload photos of signed athletes associated with PlayUp | Screen shots of PlayUp Live | Athletes/ambassadors photos | Links to athlete photos and you tube videos | Links to athlete YouTube videos & photos from PR event | Daily | Daily | Daily | Daily | Daily | Daily | Daily | Daily | Daily | Daily | Daily | Daily | Daily | Daily | Daily | Daily
| Photo Strip | Featured at top of page. Use as call to action. Feature product images, contests, etc. | Weekly | Weekly | Weekly | Weekly | Weekly | Weekly | Weekly | Daily - Upload photos of our athletes using PlayUp Live, Upload PlayUp Live on Campus pics | Upload athlete photos, endorsing PlayUp | Upload photos of on-campus games & comps | Upload photos of on-campus game & comps | Photos of winning design jersey collage contest |  | Weekly | Weekly | Weekly | Weekly | Weekly | Weekly | Weekly | Weekly | Weekly | Weekly | Weekly | Weekly | Weekly | Weekly
| Message | Make it interactive. Two-way conversations. Use as tool for feedback. | Daily | Daily | Daily | Daily | Daily | Daily | Daily | Offer help on PlayUp Live downloading and use | Daily | Daily | Daily | Daily | Daily | Daily | Daily | Daily | Daily | Daily | Daily | Daily | Daily | Daily | Daily | Daily | Daily | Daily | Daily
| Contests | Run a creative campaign to generate buzz and provide incentives for participation | 2011-06-27: Mini-contents within posts (2-3x a week); 2011-07-04: Mini-contents within posts (2-3x a week); 2011-07-11: "Refer-a-friend" Sweepstakes built growing Facebook Fan base, ends Sunday before PlayUp Live launches; 2011-08-15: Sweepstakes built - we'll send you and 5 friends to your favorite college teams bowl game - ultimate experience
| Profiles/leaderboards | Feature our weekly leaders on Facebook page | 2011-08-15: "PlayUp Fan of the week" - photo based - will appear on FB page on top left-hand side; 2011-09-26: Weekly
| Tutorial | How does PlayUp work? | 2011-07-04: Prepare script for Anthony/ Upload new GameJ tutorial video; 2011-07-18: Upload Anthony's PlayUp Live production; 2011-08-15: "PlayUp Live" tutorial featured on PlayUp Page; 2011-09-26: Updated as new products/upgrades are available; 2011-10-03: Updated as new products/upgrades are available; 2011-11-07: Updated as new products/upgrades are available; 2011-12-05: Updated as new products/upgrades are available
| Fan Gate | Tab that displays one type of content to Fans of the page, and a different type of content to non-Fans. Used as hook to generate "Likes" | 2011-06-27: Upload Mike's image - keep up until sweepstakes built; 2011-07-11: Switch out Mike's Fan Gate with picture of PlayUp Live - tie in above sweepstakes; 2011-08-15: Fan Gate built with links to all potential app stores to download PlayUp Live - sweepstakes above also included within Fan Gate
| Tabs/Applications | Used to drive fan participation and social sharing, along with promotional giveaways. Displayed on left-hand column of Facebook page. | 2011-06-27: "Card KO" uploaded; 2011-07-04: "GameJ" uploaded; 2011-07-11: "Refer-a-friend" sweepstakes application built (see above), other quizzes/games; 2011-08-15: "PlayUp" Tab - features video tutorial, user experience, links to app stores, brand ambassadors etc.
| Ads | Target users with the intent to drive "Likes" and subsequently, PlayUp games users | 2011-08-15: Work with Guy on aggressive buy of ad-words around PlayUp Live
| Target Audience | Identify and refine target audience. | 2011-06-27: Create 5 ad messages to sample; 2011-07-04: Launch 5 ad campaigns and evaluate success of each; 2011-08-15: Customized ads built to drive users to PlayUp Sports Facebook page
| Creative/Branding | Create Ads campaign that encourages people to take an action (that will be seen by their friends). Design unique images for ads. Keep text simple. | 2011-06-27: Create 5 test images for ads; 2011-08-15: Work with Mike (or creative agency) to create different samples and try different methods to see what works
| Media Buy | Purchasing time and ad space to increase brand awareness | 2011-07-25: Sketch out ad-buy (costs, impressions, etc.) during PlayUp push; 2011-08-15: Implement ad buy strategy developed in previous weeks
Twitter | bar: 2011-08-15 to 2011-09-19
| Tweets | Use as a general marketing and public relations channel by increasing customer touch points - listen, respond, engage, share, etc. | Aggressive uplift of content - office tweets, sports-tweets | Multiple times a day - will feature office updates, GameJ games, all business-related updates, retweets, etc. | [5 empty] | Constant updates- RT's of talent tweets, videos, contests, etc. | [5 empty] | Daily | Daily | Daily | Daily | Daily | Daily | Daily | Daily | Daily | Daily | Daily | Daily | Daily | Daily
Google
Search
| Key Words | Adwords & Landing page word placement (Mike)> appear at the top of all relevant Google searches (e.g football game. Mobile game. PlayUp. Play live)> increase flow to landing page |  |  | Work with Guy to define for PlayUp Live | Weekly | Weekly | Weekly | Weekly | PlayUp Live now featured PlayUp USA page - work with Guy | [5 empty] | Weekly | Weekly | Weekly | Weekly | Weekly | Weekly | Weekly | Weekly | Weekly | Weekly | Weekly | Weekly | Weekly | Weekly
| Buy | Google ads & Admob> Ads appear on the side of a Google search and in mobile applications. >increases first-time users & brand awareness |  |  | Admob - buy specifically to Iphone users | Weekly | Weekly | Weekly | Weekly | Aggressive push around PlayUp Live - work with Guy to test different methods | [5 empty] | Weekly | Weekly | Weekly | Weekly | Weekly | Weekly | Weekly | Weekly | Weekly | Weekly | Weekly | Weekly | Weekly | Weekly
| Non-paid search | Improve the quality аnd thе volume οf thе traffic tο a site bу improving thе sites ranking within a search | Identify all areas of business that can be constructed to interlink "PlayUp" ex: Card KO |  | Daily - as products/content is generated | Daily - as products/content is generated | Daily - as products/content is generated | Daily - as products/content is generated | Daily - as products/content is generated | Continue to build "PlayUp" into all content, increasing SEO | [5 empty] | Daily - as products/content is generated | Daily - as products/content is generated | Daily - as products/content is generated | Daily - as products/content is generated | Daily - as products/content is generated | Daily - as products/content is generated | Daily - as products/content is generated | Daily - as products/content is generated | Daily - as products/content is generated | Daily - as products/content is generated | Daily - as products/content is generated | Daily - as products/content is generated | Daily - as products/content is generated | Daily - as products/content is generated
YouTube
Story
| Video | Comedic "viral" concepts, events, "stories," etc. Builds brands awareness to new users, increases loyalty amongst current users, generates sharing amongst friends | 2011-08-01: Work with CAA on Viral video concept including talent; 2011-08-15: Videos uploaded from talent and ambassadors on YouTube page, along with other social media assets. Viral video published with Tier 1 Talent Partner; 2011-09-26: Weekly; 2011-10-03: Weekly; 2011-10-10: Weekly; 2011-10-17: Weekly; 2011-10-24: Weekly; 2011-10-31: Weekly; 2011-11-07: Weekly; 2011-11-14: Weekly; 2011-11-21: Weekly; 2011-11-28: Weekly; 2011-12-05: Weekly; 2011-12-12: Weekly; 2011-12-19: Weekly; 2011-12-26: Weekly
| Tutorial | Explaining step-by-step format how PlayUp Live works |  | GameJ Tutorial built |  | Meet with Anthony to discuss PlayUp Live tutorial - built by week's end | "PlayUp Live" video uploaded | [8 empty] | Weekly | Weekly | Weekly | Weekly | Weekly | Weekly | Weekly | Weekly | Weekly | Weekly | Weekly | Weekly | Weekly | Weekly
| Distribution Vehicles | Will also embed YouTube creations into social platforms, apps, website, etc. | 2011-07-04: YouTube Page designed featuring PlayUp; 2011-07-18: Upload to PlayUp assets and other pre-determined distribution assets; 2011-07-25: Use partners inventory to push video
Bloggers
| List | Build, maintain, and update blogger database for outreach. Identify forums and message boards where games are discussed (our games, social games, fantasy games) with goal being to establish relationships and footprint in these areas | 2011-06-27: Database built containing ALL college sports bloggers; 2011-07-04: Updated database of all sports bloggers (NFL,MLB, NBA,NHL) - Contact 200 bloggers and introduce $1/download; 2011-07-11: Gamer database built -contact at least 50 bloggers and introduce $1/ download; 2011-07-18: Finalize agreements with at least 10 bloggers - Trail PayPerPost; 2011-07-25: Execute; 2011-08-15: Execute; 2011-09-26: Execute; 2011-11-07: Execute
| Agreements/Output | Reach incentive-based agreements with bloggers | 2011-06-27: Define Milestones / Draft outline of what agreement will look like; 2011-07-04: Contact bloggers where we hold relationships - offer $1 download to all bloggers; 2011-07-11: Finalize Agreements with at least 15 bloggers; 2011-07-18: Finalize agreements with additional 5 bloggers; 2011-07-25: Execute; 2011-08-15: Media blitz based on download incentives, 15 additional deals achieved; 2011-09-26: Execute; 2011-11-07: Execute
Enablers
| Deepmile | Determine where our target demographic lies. Gives us the ability to market directly to the users most likely to play/ become loyals. | 2011-06-27: JP - Define Milestones / Proposal; 2011-07-04: Sign Agreement; 2011-07-11: Enablers defined (will influence CAA talent deals); 2011-07-18: Activate Plan; 2011-07-25: Engage; 2011-08-15: Heavy social blitz of enablers with defined message around PlayUp Live; 2011-09-26: Execute; 2011-10-03: Execute; 2011-10-31: Execute; 2011-11-28: Execute; 2011-12-26: Execute
| Fiksu | Ability to place the PlayUp app into top 10. Generate brand awareness and increase app downloads > Aims to increase users/ first-timers. | 2011-06-27: JP - Define Milestones / Proposal; 2011-07-04: Sign Agreement; 2011-07-18: Activate Plan; 2011-07-25: Engage; 2011-08-15: PlayUp Live pushed to top of App stores across all platforms; 2011-09-26: Execute; 2011-10-03: Execute; 2011-10-31: Execute; 2011-11-28: Execute; 2011-12-26: Execute
Partnerships
| Leagues | Develop professional sports league partnerships (CAA/SMA) | 2011-06-27: Meeting with NFL; 2011-07-04: Set up meetings with Pac 10 and Big 10 Conferences; 2011-07-25: Meet with at least 1 conference; 2011-08-15: Finalize 1 conference deal
| NCAA Universities | Partner with at least 5 universities | Introduce PlayUp Live concept to CAA - understand University benefits | Establish contact with at least 15 universities | Pitch Universities (5 min.) | Dial in on agreements |  | 5 deals finalized with Universities | Execute Agreement - website, stadium tents, banners, Game Day, radio, etc. |  |  | Activate - social media partnerships (contests/sweepstakes), Official Fan Engagement Partner on jumpotron and led screens, PlayUp tents at all stadiums, cover of programs, email marketing campaigns |  |  |  | Weekly Activation | Weekly Activation | Weekly Activation | Weekly Activation | Weekly Activation | Weekly Activation | Weekly Activation | Weekly Activation | Weekly Activation | Weekly Activation
| NFL Teams | Partner with at least 3 teams (CAA) | Define Milestones/ Meeting with Jeff to review all NFL proposals (10-15), prepare next steps | Proposals exchanged/ Pitch 8 NFL teams | Meeting with NY Giants @ 11am / set up meetings with additional 3 teams that week | Dial in on agreements |  | 3 NFL Team Partnerships finalized | Execute Agreement - website, stadium tents, banners, Game Day, radio, etc. | "Official Fan Engagement Partner" established on teams website - links to website installed |  | Activate - social media partnerships (contests/sweepstakes), tailgates, Official Fan Engagement Partner on jumpotron and led screens, PlayUp tents at all stadiums, cover of programs, email marketing campaigns |  |  |  | Weekly Activation | Weekly Activation | Weekly Activation | Weekly Activation | Weekly Activation | Weekly Activation | Weekly Activation | Weekly Activation | Weekly Activation | Weekly Activation | Weekly Activation | Weekly Activation | Weekly Activation | Weekly Activation
| Marketing Partner | Identify key marketing partner to embed our products as part of their sports marketing campaigns (CAA) | 2011-06-27: Identity targets with CAA (15 min); 2011-07-04: Put Pitch Proposal together; 2011-07-11: Start to Pitch it - 10 proposals by EOW; 2011-07-18: Receive feedback - 5 additional proposals out; 2011-08-15: Marketing Partner Locked in
| Media | Investigate potential role of media partner as source of marketing and distribution (SMA) | 2011-07-04: Identify potential media outlets where we have relationships, introduce partnerships GameJ; 2011-07-11: Target 10 RSN's to pitch; 2011-07-18: Initial pitch to 10 RSN's; 2011-07-25: Meet with 4 RSN's; 2011-08-08: Finalize agreements with 2 RSN's by August 8th; 2011-08-22: Draft new list of 8 targets for RSN's, initiate contact; 2011-09-05: Meet with 4 RSN's; 2011-09-19: Finalize agreement with additional 2 RSN's - NHL or NBA
| Talent | Team up with a sport star or celeb to promote games. Talent becomes 'face' of PlayUp, users associate them with us > Generates buzz, builds brand image and increase users. (CAA) | 2011-06-27: Define milestones (metrics) / Introduce PlayUp Live to CAA, $1/DL; 2011-07-04: Identify 100 athletes we want to target as partners across all spectrums - big name on college campus, heavy social following, personable, hungry, $1DL; 2011-07-11: Pitch 50 prospective athletes on PlayUp Live partnerships, $1/DL; 2011-07-25: Finalize agreements with min. 10 athletes; 2011-08-01: Agreement with Tier 1 talent - heavy digital and university based presence, finalize agreements with additional 10 Tier 2/3 athletes, push talent to execute agreement; 2011-08-08: Finalize agreement with additional 10 athletes (bringing count to 30), Execute; 2011-08-15: 30 Tier 2/Tier 3 athlete deals signed by August 15 - Talent blitz across all social media assets, viral video production, PR, $1/download incentive, provide specific instructions to talent on how to increase engagement, draw followings, make $, big event on NCAA/NFL kickoff weekend
| Charity | Identify cause related overlay into game products and marketing | 2011-08-08: Finalize Charity Plan; 2011-11-21: PlayUp Live Thanksgiving Dinner for ___ family; 2011-12-19: Xmas party for troops abroad sponsored by PlayUp
PR
| WOW | Find Agent. Unique & creative launch concepts. Get peoples attention, Kick ass promotion. |  | Introductory conversations with 5 PR candidates / define milestones | Interview Candidates (3) | Finalize PR agreement | Begin Activation of Plan around Launch of PlayUp Live on Iphone, including $1/download | Prepare plan for August 15th launch |  | PR blitz across all relationships | [5 empty] | Weekly | Weekly | Weekly | Weekly | Weekly | Weekly | Weekly | Weekly | Weekly | Weekly | Weekly | Weekly | Weekly | Weekly
| Talent | Team up with a sport star or celeb to promote games. Talent becomes 'face' of PlayUp, users associate them with us > Generates buzz (tweet), builds brand image/awareness and increase users. | 2011-08-01: Press Release around signing of Tier 1 Athlete; 2011-09-05: Min. 3 athletes to appear at PlayUp Live Launch Event; 2011-09-12: ALL Pro athletes participating in PlayUp during respective NCAA games
| Special Events | Host bar events, game nights, day competitions. Reaches out to specific demographic, creates brand awareness> Generates buzz, increase new users & user sharing- bring your friends! | 2011-08-15: Press Release for PlayUp Live out 8/15, press invites sent out for event on Kickoff Weekend; 2011-09-05: PlayUp Live Product Launch - PR Event; 2011-09-12: Weekly; 2011-09-19: Weekly; 2011-09-26: Weekly; 2011-10-03: Weekly; 2011-10-10: Weekly; 2011-10-17: Weekly; 2011-10-24: Weekly; 2011-10-31: Weekly; 2011-11-07: Weekly; 2011-11-14: Weekly; 2011-11-21: Weekly; 2011-11-28: Weekly
| Trade shows | Attend industry trade events/shows> sport, mobile and online gaming. Attending/speak at relevant shows> gives PlayUp a place within the market professionally. Brand awareness.
| Trade Outreach | Have presence in print media. News paper articles, online, message boards, gaming forums, groups, bloggers, etc.
Events/Grassroots
College Ambassador Program | College | Groups of passionate, excited students who match target demographic and will work to spread the PlayUp brand and games throughout their school. | 2011-07-04: Decision made on Firm - next steps built out; 2011-07-11: Agreement Finalized; 2011-08-15: Ambassadors reach out to networks, educate on PlayUp contest
| Ambassadors | Students who will represent PlayUp brand on college campus | 2011-07-11: Define Ambassadors- success metrics, incentives, $1/download,; 2011-07-18: Identify Ambassadors (5 per school, 20 schools); 2011-07-25: Pitch Ambassadors; 2011-08-01: Finalize Agreements with 50 Brand Ambassadors - send out information packets, legal documents, share social assets, iphones, etc.; 2011-08-15: Ambassadors reach out and educate friends/networks on PlayUp Live, hit campus - campaigns begin - social, events, product testing, giveaways, sweepstakes, contests, uploads, etc.; 2011-09-26: Conduct analysis on brand ambassadors program to date - downloads driven, Facebook "likes", pics/videos uploaded, jersey contest, etc. Tweak programs individually.
| Contests/Sweepstakes | Run a creative contest/sweepstakes to generate buzz and provide incentives for participation | 2011-08-15: "Design your college jersey" contest through Facebook and Twitter, incorporating Yugi into the design. Will increase brand awareness, downloads, social buzz around PlayUp Live. Winners are published on social media assets.; 2011-10-10: What campus can get the most "Likes" by November 7th? A university alumni will come out and cook a Thanksgiving dinner for fraternity/student organization the week before thanksgiving.
| Social Uploads | Ambassadors will generate social content by uploading videos and pictures from PlayUp events on campus | 2011-08-15: Ambassadors are each responsible for daily post on personal Facebook page, 10 pictures a week, 3 videos a week, (on both PlayUp assets and personal assets). Multimedia can be from campus events, games, with PlayUp t-shirts, etc.; 2011-10-03: Upload photos/videos from home games, midnight madness, pep-rallies, Greek life competitions away games, tailgates, road trips, special events, homecoming, etc.
| Events | Hold events on campus to generate buzz around PlayUp, generate content, and brand awareness. | 2011-08-22: Weekly Events on campus - at fraternity house, bars, tailgates, inflatable's, etc. - Work with ambassadors to understand where their ties are on campus and leverage those relationships
| Meetings/ Product Testing | Meetings will serve as touch points with ambassadors to tweak program as well as provide feedback on current products. | 2011-06-27: Interview Brand Ambassador Firms - Mr. Youth, Alliance, PGW; 2011-08-01: Phone call/Skype meeting with chosen ambassadors. Update on product & push; 2011-08-08: Phone call/Skype- update and results. Debrief on Live launch; 2011-08-15: Call/Skype each group, tweak live push dependant on 1st week results - Receive feedback on PlayUp Live; 2011-08-22: Debrief on NCAA push. Collect results on Live campaign - receive feedback from friends and ambassadors on product; 2011-08-29: Call/Skype 3 times weekly. Tweak each groups push individually.; 2011-09-05: Call/Skype 3 times (1 per time zone); 2011-10-03: Ambassadors test products and include friends/network in testing. Report feedback.
Military Program
| Ambassadors |  | 2011-12-05: GameJ Army Navy football presented by PlayUp Live; 2011-12-12: PlayUp Spokesman will welcome home troops for holidays
Stories | Unique ways to generate buzz around PlayUp |  | 2011-09-05: Sponsor/Partner sports-talk predictions of the month - 610 WIP; 2011-10-10: PlayUp Sponsors Mayor Bet- featured on PlayUp Live
Note on B57: David Brody: Change to go under Brand Ambassadors Program

## Daily Schedule
PlayUp Offering
PlayUp Story/Theme | [9 empty] | July
Dates |  | 2011-06-23 | 2011-06-24 | 2011-06-25 | 2011-06-26 | 2011-06-27 | 2011-06-28 | 2011-06-29 | 2011-06-30 | 2011-07-01 | 2011-07-02 | 2011-07-03 | 2011-07-04 | 2011-07-05 | 2011-07-06 | 2011-07-07 | 2011-07-08 | 2011-07-09 | 2011-07-10 | 2011-07-11 | 2011-07-12 | 2011-07-13 | 2011-07-14 | 2011-07-15 | 2011-07-16 | 2011-07-17 | 2011-07-18 | 2011-07-19 | 2011-07-20 | 2011-07-21 | 2011-07-22 | 2011-07-23 | 2011-07-24 | 2011-07-25 | 2011-07-26 | 2011-07-27 | 2011-07-28 | 2011-07-29 | 2011-07-30 | 2011-07-31
|  | Thurs. | Fri. | Sat. | Sun. | Mon. | Tues. | Wed. | Thurs. | Fri. | Sat. | Sun. | Mon. | Tues. | Wed. | Thurs. | Fri. | Sat. | Sun. | Mon. | Tues. | Wed. | Thurs. | Fri. | Sat. | Sun. | Mon. | Tues. | Wed. | Thurs. | Fri. | Sat. | Sun. | Mon. | Tues. | Wed. | Thurs. | Fri. | Sat. | Sun.
Events
SOCIAL MEDIA
Facebook
Page
| Content-wall | 2011-06-23: NBA Draft - Predict Top 5 in order for a giveaway; 2011-06-24: Photo Mesh; 2011-06-27: Weekly Preview of Social Media Posts; 2011-06-30: PlayUp Live hype - "Coming tomorrow, we will redfine the way you consume sports" type of post; 2011-07-01: Daily Post - Find this in PlayUp Live for prize; 2011-07-02: Daily Post - Find this in PlayUp Live for prize; 2011-07-03: Daily Post - Find this in PlayUp Live for prize; 2011-07-05: Daily Post - Find this in PlayUp Live for prize; 2011-07-06: Daily Post - Find this in PlayUp Live for prize
| Branding/Pictures | 2011-07-01: PlayUp Live uploaded; 2011-07-02: GameJ app photo uploaded
Photo Strip
| Contests | 2011-07-06: Upon Agreement: Extole Sweepstakes uploaded
| Tutorial | 2011-07-08: GameJ video uploaded
| Fan Gate | 2011-06-23: Mike is delivering FanGate w/ premis being PlayUp Games - PlayUp Live will be substituted when available; 2011-07-01: Image of PlayUp to be included in Fan Gate designed; 2011-07-05: PlayUp Live and link to app store to be included
| Applications | 2011-06-23: Facebook MiniGame developed - presented to JP for final approval; 2011-06-28: Review Extole with JP - "Refer-a-friend" - set up meeting; 2011-06-30: Phone call with Extole
Ads
Target Audience
Creative/Branding
Media Buy
Google
Search
| Key Words | 2011-06-27: Schedule call with Guy to discuss PlayUp Live; 2011-07-01: Schedule Call to follow up on PlayUp Live Planning
| Buy | 2011-07-04: PlayUp Live Ad Words campaign kicks off
YouTube
Story
| Video | 2011-06-29: Anthony presenting viral concepts in paperform - David to discuss with JP
| Tutorial | 2011-07-01: Anthony reviewing GameJ app; 2011-07-06: GameJ video tutorial produced; 2011-07-07: GameJ video uploaded to all PlayUp assets
Distribution Vehicles
Bloggers
| List | 2011-06-23: Database constructed of all BCS-related bloggers (6 conferences, 10-12 schools each); 2011-06-24: Database constucted identifying all NFL teams and their related bloggers
| Content | 2011-06-27: Reach out to BCS bloggers to gauge interest on $1/download of PlayUp Live
Ads
Enablers
| Deepmile | 2011-06-28: JP iniates discussion with Deepmile aroudn PlayUp Live
Fixsu
Partnerships
Leagues
| Teams | 2011-06-23: Provide JP with latest update on NFL teams (Panthers, 49ers, Cardinals, Cowboys, Seahawks, Broncos); 2011-06-30: Meeting with CAA presenting excel file outling all teams proposals to date to easily compare and contrast offers; 2011-07-11: Meeting with NY Giants - 11am
Marketing Partner
Media
| Talent | 2011-06-30: Discuss B and C level talent endorsments/partnerships of PlayUp Live; 2011-07-05: Review PlayUp Live and dial in on what specifics of partnership; 2011-07-07: Review CAA's proposal of talent for PlayUp Live Partnership; 2011-07-14: Talent Agreement for PlayUp Live
Charity
PR
WOW
Talent
Twitter
Special Events
Trade shows
Trade Outreach
Events/Grassroots
Ambassador Program
| College | 2011-06-28: Phone call with Promotions Group West; 2011-06-29: Meeting with Mr. Youth - introduction coming from CAA
Corporate
Stories
Mayor
Team Theme Song
Who's Next
Memorable Moments
Sports radio report card
Rap for your team